28 April 2022

Mitchell Williams u18013555

EPR402 Project Progress Meeting #3 (Group Meeting)

NetLab B

* Agenda: Discuss project proposal, budgets and general progress update
* Half students’ proposals ready to be signed off and a few need to do some more work
* Submission is due 4th May for proposal at midnight
* Individual meetings next week – proposal language edited by next week
* Checkout of lab book at each individual meeting – your deadline time is your meeting time
* Budgets – money available for group as a whole - a departmental budget that can be used if multiple people need same component – hardware stays in hardware store post-project
* Next milestone – generate a provisional budget for project
* Budgets usually due in mid-May – have to fill in claim form to get money back later in year
* Potentially free 3D printing in study center for Project
* First formal literature review due at start of second semester alongside first semester report and Project plan – work on it sooner as one of the project milestones
* Plan a month in second semester for final report
* Don’t underestimate ERP + workload in second semester
* Mr. Grobler will discuss outline of final report in mid-October in an individual meeting
* 10th May – Group meeting where all students will present their project with a slideshow and describe their project and progress
* Show debugging + how your project actually works under the hood – what is the project doing and show underlying processes – extra marks in final project demo
* Mitch project - amount of software to implement from first principles is substantial and so needs to be worked on as soon as possible
* Hardware projects – get your components and design done soon so can acquire hardware